Administrative Office of the United States Courts

BPA for TSO Support Services

Contract Number 47QTCA20D00C6

# Monthly Status Report

June 2026

Reporting Period: June 1- 30, 2026

# Call Order 002 – Enterprise Architecture (EA) Support

## Funding Information*

| Funds Obligated | $3,225,811.68 |
| --- | --- |
| Funds Expended to Date | $1,695,515.53 |
| Funds Remaining | $1,530,296.15 |
| Estimate at Completion | $3,087,893.53 |
| Over/Under | $137,918.15 |

## Monthly Activity

#### Activities completed for the current reporting period

- Technical Architecture (As Is): Continued development and refinement of Enterprise Architecture (EA) As-Is dashboards. Coordinated with Dynatrace on API integration and runtime validation planning. Advanced Technology Reference Model (TRM) lifecycle governance by refining evaluation criteria and hierarchy alignment based on stakeholder feedback and governance reviews.

- IT Application and Systems Authentication Standard: Completed review activities and submitted the standard for EAMB approval. Publication on JNET and SharePoint is pending approval.

- Blue Folder and Judiciary-Wide Review Process: Completed revisions to the Blue Folder and Judiciary-Wide Review process to align with updated workflows and organizational changes. Updated supporting process documentation and checklists.

- IT Standards Center of Excellence (COE): Completed SharePoint site layout and wireframe development. Conducted multiple stakeholder demonstrations to collect feedback on navigation and user experience, incorporating refinements based on input received. Prepared the site for final demonstration and User Acceptance Testing (UAT).

- IT Public Cloud Standard: Continued development of the standard through collaborative sessions focused on requirements analysis, content development, and stakeholder alignment.

- IT Vulnerability and Patch Management Standard: Continued development of the standard through stakeholder engagement, requirements refinement, and content development activities.

- Security Domain: Continued development of the Controlled Unclassified Information (CUI) Policy Framework to support Data Loss Prevention (DLP) requirements and guidance. Completed the Future of Infrastructure and CM/ECF Executive and Technical documents and submitted them for leadership review.

- IT Standards Maturity Model: Conducted working sessions and presented the maturity model to leadership. The model is currently undergoing final review prior to publication on the IT Standards Center of Excellence (COE) SharePoint site.

- Judiciary IT Standards Documentation Update: Continued progress on the COE template library, with most templates drafted and under review. The library will provide standardized artifacts that support the end-to-end IT standards lifecycle and promote consistency across standards initiatives.

#### Activities planned for the following reporting period

- Technical Architecture (As Is): Continue enhancement of EA As-Is dashboards through coordination with the OTIS team to implement a JSON REST API for automated daily VM metadata refreshes, replacing manual CSV extracts. Continue Dynatrace API integration and runtime validation activities. Finalize TRM lifecycle governance refinements and develop a presentation outlining governance workflows and stakeholder expectations.

- IT Application and Systems Authentication Standard: Support publication activities upon receipt of EAMB approval.

- Blue Folder and Judiciary-Wide Review Process: Project completed; no additional activities planned.

- IT Standards Center of Excellence (COE): Conduct the final stakeholder demonstration, complete UAT activities, and prepare the site for production deployment.

- IT Public Cloud Standard: Finalize the initial draft of the standard and submit it for SME review and feedback.

- IT Vulnerability and Patch Management Standard: Finalize the initial draft of the standard and submit it for SME review and feedback.

- Security Domain: Continue assessment activities related to VMware replacement efforts and advance development of the Controlled Unclassified Information (CUI) Policy Framework supporting Data Loss Prevention (DLP) requirements.

- IT Standards Maturity Model: Complete final review activities and publish the maturity model on the IT Standards Center of Excellence (COE) SharePoint site.

- Judiciary IT Standards Documentation Update: Complete the remaining COE templates and publish the template library to support standardized standards development, governance, review, and publication activities.

| Division | EA Staff | Start Date | TSO LCAT |
| --- | --- | --- | --- |
| Enterprise Arch | Amit Yadav | 10/3/2022 | Sys Integration Engr |
| Enterprise Arch | Chris Harkins | 11/1/2022 | Sys Integration Engr |
| Enterprise Arch | Vidyadhar Tanksale | 03/13/2023 | Enterprise Architect |
| Enterprise Arch | Alisa Welch | 10/24/2022 | Business Analyst |
| Enterprise Arch | Alec Gura | 7/10/2023 | Communications Specialist |
| Enterprise Arch | Jason Guglietta | 12/4/2023 | Systems Integration Engineer |
| Enterprise Arch | Sudeep Telang | 11/5/2024 | Enterprise Architect |
| Enterprise Arch | Navin Keswani | 11/4/2024 | Systems Integration Engineer |
| Enterprise Arch | Ranga Lakshminarayanan | 4/6/2026 | Cloud Architect |
| Enterprise Arch | Ramajyothi Indukuri | 11/18/2024 | Business Analyst |
| Enterprise Arch | Zakariya Saleh | 12/9/2024 | Systems Architect |
| Enterprise Arch | Yenenesh Shewaneh | 3/25/2025 | Data Architect |
| Enterprise Arch | Carl Mosca | 12/8/2025 | Systems Integration Engineer |
| Enterprise Arch | Ceenil Kaur | 12/15/2025 | Project Manager |
| Enterprise Arch | Moiz Khan | 10/15/2024 | Systems Integration Engineer |

## Requested travel during the following reporting period

- N/A

## High Priority Issues

- N/A

## High Priority Risks

Risk: Schedule Adjustment: A 30–60 day schedule extension may be required for the IT Public Cloud Standard and IT Vulnerability & Patch Management Standard to accommodate additional development, stakeholder review, and EAMB approval activities.

# Call Order 004 – MFA Support

## Funding Information*

| Funds Obligated | $1,903,545.60 |
| --- | --- |
| Funds Expended to Date | $1,470,887.63 |
| Funds Remaining | $432,657.97 |
| Estimate at Completion | $1,510,035.15 |
| Over/Under | $393,510.45 |

## Monthly Activity

#### Activities completed for the current reporting period

- MFA Support: Continued operational support across MFA initiatives, including Login.gov onboarding support, application team coordination, and vulnerability remediation activities. Supported OSCAR Login.gov planning efforts through recurring working sessions, application walkthroughs, questionnaire reviews, and documentation updates. Resolved longstanding DUO support issue impacting MacOS offline authentication and completed remediation of remaining vulnerability items. Continued development and refinement of provisioning and operational support documentation.

- WHfB: Continued troubleshooting and escalation efforts with Microsoft related to on-premises Certificate Trust enrollment and authentication issues. Collected and provided additional logs to Microsoft engineering teams, updated hybrid deployment documentation, and continued internal analysis for on prem issue resolution.

- PIV-I for VPN: Advanced project closeout activities through stakeholder review and recommendation package updates. Coordinated review cycles with Michael Keyes, EA Team, and ISO stakeholders. Updated recommendation document and finalized supporting deliverables in preparation for formal project closure.

- Adaptive Authentication: Progressed Proof of Concept (POC) implementation activities through ISVA installation and configuration, adaptive authentication use case development, conditional access policy configuration, and lab environment expansion. Completed adaptive authentication testing scenarios (Adaptive auth for Zscaler VPN, adaptive auth outcomes for windows desktop login experience, and conditional access risk-factor evaluations.) And have developed supporting test-lab documentation and configuration guidance as tasks are completed.

- Elevated Access: Continued development of current-state architecture documentation, process flows, and gap analysis activities in coordination with CyberArk stakeholders. With plans to refine project scope, schedule, and supporting documentation to align with CyberArk data that is being provided and emerging stakeholder requirements. Progressed environment access coordination and testing preparation activities to support future-state architecture documentation and testing.

- YubiKey: Project formally closed. Completed lessons learned documentation, archived project artifacts, finalized stakeholder communications, and transitioned deliverables into long-term reference documentation status.

- EA As-Is: Continued development and refinement of EA As-Is dashboards, coordination with Dynatrace related to API integration and runtime validation planning. Continued refinement of TRM lifecycle governance, evaluation criteria, and hierarchy alignment based on stakeholder feedback and governance review activities.

#### Activities planned for the following reporting period

- MFA Support: Continue Login.gov onboarding support and coordination activities, vulnerability tracking activities, refining templates to use across all projects, and updating VM processes.

- WHfB: Continue Microsoft escalation efforts and engineering coordination to resolve remaining on prem issues and close out on-prem resolution. Complete hybrid documentation updates.

- Adaptive Authentication: Continue development and execution of adaptive authentication use cases within the lab environment. Expand conditional access policy testing, validate additional authentication scenarios, and continue development of POC findings and recommendations.

- Elevated Access: Complete current-state assessment activities, finalize current state assessment and gaps, refine scope, architecture diagrams, and implementation considerations based on stakeholder feedback and start working on future-state architecture development.

- YubiKey: No planned activities. Project closed.

- PIV-I for VPN: No planned activities. Project Closed.

- EA As-Is: Continue refinement of EA As-Is dashboards via coordination with OTIS team to build JSON REST API to receive daily refresh of VM metadata to replace manual CSV extracts, coordination with Dynatrace related to API integration and runtime validation planning. complete refinement of TRM lifecycle governance based on stakeholder feedback and governance review activities and develop presentation to share TRM Governance flow expectations.

## MFA Support Employee Listing

| Division | Staff | Start Date | TSO LCAT |
| --- | --- | --- | --- |
| Service Delivery | Muhammad Nazir | 5/22/2023 | System Integration Engineer |
| Service Delivery | Sunil Bandapally | 7/10/2023 | Systems Integration Engineer |
| Service Delivery | Narayan Verma | 7/17/2023 | Systems Integration Engineer |
| Service Delivery | Sangameswar Gupta | 6/17/2024 | Systems Integration Engineer |
| Service Delivery | Lauryn Holcomb | 8/7/2023 | Project Manager |
| Service Delivery | Karaman Talibov | 1/20/2026 | Systems Integration Engineer |

## Requested travel during the following reporting period

- N/A

## High Priority Issues

Issue: WHfB: Ongoing Microsoft support coordination for on-premises Certificate Trust authentication failures continue to delay completion of validation activities.

Resolution: Continued escalation with Microsoft engineering teams, submission of additional diagnostic logs, and parallel internal troubleshooting efforts to isolate root cause and maintain project momentum.

Issue: MFA Support: Login.gov onboarding and support activities continue to require recurring coordination across multiple application teams, creating competing priorities for project resources.

Resolution: Continued use of recurring working sessions, centralized documentation, and coordinated stakeholder engagement to improve onboarding efficiency and reduce implementation risk.

## High Priority Risks

Risk: WHfB: Continued dependency on Microsoft engineering support and supporting infrastructure components (ADFS, Certificate Services, and Entra ID) may impact project timeline and final validation activities.

Mitigation: Maintain escalation pathways, continue recurring support engagements, and pursue parallel validation and documentation activities where feasible.

Risk: MFA Support: Ongoing support demands, vulnerability remediation activities, and application onboarding efforts may compete with project execution timelines across the MFA portfolio.

Mitigation: Continue centralized tracking and prioritization of support activities through JIRA dashboards, recurring coordination meetings, and workload management processes.

EA As-Is: Risk (1): Organizational restructuring and evolving governance responsibilities may create ambiguity around ownership of business capabilities, application stewardship, and technology domains, impacting accountability and decision-making across the EA As-Is initiative.

Mitigation (1): Continue development and enforcement of the EA governance model, RACI matrix, and Architecture Review Board (ARB) processes to formally document ownership, accountability, and decision authority across workstreams.

EA As-Is: Risk (2): Application, infrastructure, and technology data may remain fragmented or inconsistent across CSAM, CMDB, OTIS, Dynatrace, and program office inventories, potentially impacting the accuracy and completeness of the enterprise architecture baseline.

Mitigation (2): Establish a centralized authoritative EA repository, continue phased data normalization and validation activities, and implement standardized terminology, lifecycle definitions, and governance processes across contributing data sources.

# Call Order 013 – DevSecOps

## Funding Information*

| Funds Obligated | $1,425,043.20 |
| --- | --- |
| Funds Expended to Date | $744,032.29 |
| Funds Remaining | $681,010.91 |
| Estimate at Completion | $1,417,469.17 |
| Over/Under | $7,574.03 |

## Monthly Activity

#### Activities completed for the current reporting period

- Investigated implementation approaches for OpenTelemetry, Kubernetes RBAC, VMware Infrastructure as Code (IaC), and internal certificate auto-renewal to provide recommendations that support improved observability, least-privilege access, infrastructure automation, and certificate lifecycle management.

- Strengthened the security posture of platform components by cleaning up Log4j and OpenJDK 21 vulnerabilities in custom images, updating the Selenium Hub Java base image, and addressing critical Containered vulnerabilities identified in the Splunk report to reduce security risks and maintain supported software versions.

- Advanced DevSecOps automation by configuring a Git event-based deployment pipeline and integrating SonarQube, Fortify, and Black Duck with the InfoWeb chat application, enabling automated deployments and improved application security scanning.

- Developed an assessment form based on identified requirements, reviewed it with the Product Owner and stakeholders, and incorporated feedback to improve the quality and readiness of the assessment before distribution.

- Investigated and documented approaches for managing existing and new VMware virtual machines using Infrastructure as Code, providing implementation guidance, best practices, and reusable patterns to support consistent and scalable infrastructure management.

#### Activities planned for the following reporting period

- Complete the evaluation of container/Dockerfile vulnerability scanning tools and implement Cosign digital signing in the CI/CD pipeline to strengthen container security, improve software supply chain integrity, and document recommended tooling.

- Create a Kubernetes Dashboard UI, externalize Helm values into environment-specific ArgoCD configurations, and implement branch/tag-based environment promotion logic to improve deployment visibility, standardize release management, and automate CI/CD workflows.

- Upgrade Fortify from version 21 to version 26, including preparing the licensed Docker image and publishing it to Artifactory, to restore vendor support, maintain secure code scanning capabilities, and ensure continued platform compatibility.

- Continue reviewing the assessment form with stakeholders, investigate Developer Portal support for VM applications, and test Selenium Hub when a stable OpenJDK version is available to incorporate stakeholder feedback, evaluate future platform capabilities, and prepare automated testing infrastructure.

- Remediate the OpenSSL vulnerability on the PostgreSQL server and sandbox cluster by updating the affected RHEL packages to address critical security vulnerabilities and improve the security posture of the environment.

## DevSecOps Employee Listing

| Division | Staff | Start Date | TSO LCAT |
| --- | --- | --- | --- |
| Service Delivery | Vijay Sivaprakasam | 9/30/2024 | Systems Integration Engineer |
| Service Delivery | Harsh Jain | 11/25/2024 | Systems Integration Engineer |
| Service Delivery | Madhur Gupta | 4/16/2025 | Business Analyst |
| Service Deliver | Shailendra Gohil | 3/22/2024 | Systems Integration Engineer |
| Service Delivery | Olusola Awoderu | 12/26/2023 | Software Engineer |
| Service Delivery | Mohana Molabanti | 8/28/2023 | Cloud Architect |

## Requested travel during the following reporting period

- N/A

## High Priority Issues

- N/A

## High Priority Risks

- N/A

# Call Order 015 – Innovation & Research

## Funding Information*

| Funds Obligated | $1,853,995.87 |
| --- | --- |
| Funds Expended to Date | $744,603.44 |
| Funds Remaining | $1,109,392.43 |
| Estimate at Completion | $1,378,035.44 |
| Over/Under | $475,960.43 |

## Monthly Activity

#### Activities completed for the current reporting period

- Continued deploying the JEFS internal site to Azure Kubernetes Service as proof of concept and cloud cost evaluation.

- Continued development of the InfoWeb Support Guide Chatbot, focusing on usability and integration with existing documentation.

- Completed development assistance of the ARC Hub, expanding semantic search and summarization capabilities.

- Completed development assistance of the CVB solution, progressing structured data extraction capabilities.

- Completed development assistance of the cross-cloud PDF text extraction capability toward broader applicability across use cases.

- Continued refinement of Courtney and the Online Judicial Guide in alignment with AO priorities.

- Continued working with AO leadership to define and formalize the operating model, ensuring clear direction and execution alignment.

- Completed moving current and existing POCs to OpenShift

- Continued assessing and creating automated testing procedures for LLM projects

- Started created a testing suite of applications and questions for the Judiciary Guide using Garak and DeepEval.

#### Activities planned for the following reporting period

- Continue deploying the JEFS internal site to Azure Kubernetes Service as proof of concept and cloud cost evaluation.

- Continue development of the Infoweb Support Guide Chatbot, focusing on usability and integration with existing documentation.

- Continue refinement of the Online Judicial Guide in alignment with AO priorities.

- Continue working with AO leadership to define and formalize the operating model, ensuring clear direction and execution alignment.

- Continue creating a testing suite of applications and questions for the Judiciary Guide using Garak and DeepEval.

- Continue assessing and creating automated testing procedures for LLM projects

## Innovation & Research Support Employee Listing

| Division | Staff | Start Date | TSO LCAT |
| --- | --- | --- | --- |
| Service Delivery | Kenneth Megill | 10/7/2024 | Business Analyst - Senior |
| Service Delivery | Louden Motina | 4/1/2025 | Enterprise Architect |
| Service Delivery | Jason De Kock | 10/7/2024 | Systems Integration Engineer |
| Service Delivery | Louie Chen | 11/12/2024 | AI Engineer |
| Service Delivery | Syed Abbas | 8/11/2025 | Information Assurance Engineer |
| Service Delivery | Dhruvi Rathod | 8/14/2025 | Information Assurance Engineer |

## Requested travel during the following reporting period

- N/A

## High Priority Issues

Issue: Operating model and decision alignment across AO and TechSur remain in definition as part of the ongoing leadership transition.

Resolution: Continue regular engagement with TechSur and AO leadership to monitor engagement and reflection of shared operating model that defines direction, decision-making, and execution expectations.

## High Priority Risks

Risk: TSO cloud capabilities are still maturing and may not yet fully support all targeted innovation use cases.

Mitigation: Continue aligning development efforts to currently available TSO services while informing a multi-cloud strategy that ensure access to the full range of capabilities required for advanced and emerging innovation use cases.

# Call Order 016 – RAE Support

## Funding Information*

| Funds Obligated | $3,383,404.80 |
| --- | --- |
| Funds Expended to Date | $533,577.96 |
| Funds Remaining | $2,849,826.84 |
| Estimate at Completion | $3,260,861.72 |
| Over/Under | $122,543.08 |

## Monthly Activity

### Business Operations (Compliance)

#### Activities completed for the current reporting period

- Project Management & PMO Support

  - Provided PMO support to TSIO, including PM process improvement workshops, contract deliverable verification, project inventory assessment, and ongoing PM guidance. Worked to transition existing work for new Agile Coach.

  - Continued PM support for the Sealed Document Security (SDS) Project, including schedule updates, stakeholder coordination, meeting facilitation, action tracking, and support for transition activities.

  - Provided PM support for the ETSD AI Strategy Initiative, AI Gateway, Courtroom Technology

  - Began onboarding new Agile Coach resource, Ram Dasari

- Governance, Security & Vulnerability Management

  - Conducted daily monitoring and analysis of vulnerability reports and tracked remediation progress for critical and high-risk findings.

  - Resolved reporting inaccuracies by eliminating false-positive vulnerability plugin IDs from Splunk reporting.

  - Coordinated installation and remediation of missing Nessus agents across identified systems.

  - Partnered with DevSecOps and Development teams to remediate JDK vulnerabilities and resolve reopened findings.

  - Addressed asset inventory discrepancies, including CSAM ID corrections, decommissioned asset validation, and CMDB updates.

  - Developed and refined Vulnerability Management Policy and SOP documentation.

  - Delivered Azure Minimum Controls guidance and completed JSIF/Azure control mapping.

  - Provided security-related recommendations, stakeholder feedback, and completed required annual security training.

- DevSecOps & Automation

  - Implemented Git event-based deployment pipelines supporting automated deployments across Development, Staging, and Production environments.

  - Established deployment workflows aligned with organizational branching and release management strategies.

  - Completed Infrastructure as Code (IaC) assessment for VMware environments, including Terraform and Ansible implementation guidance.

  - Conducted research into automated internal certificate renewal processes and documented recommendations for future implementation.

- Cloud & Platform Support

  - Continued support for TSO and COO teams with cloud development activities and access control management.

- Courtroom Technology Support

  - Supported FY25 Judiciary-wide data collection analysis and reporting efforts.

  - Assisted with AVoIP courtroom design reviews and Judiciary-wide stakeholder engagement activities.

  - Supported development and maintenance of Courtroom Technology SharePoint sites.

  - Assisted with courtroom technology research, meetings, and business case development.

  - Participated in the Courtroom Technology Conference and continued administration of the Judiciary’s AVIXA membership program.

#### Activities planned for the following reporting period

- Project Management & PMO Support

  - Continue PMO support for TSIO, including project process improvements and Jira process alignment.

  - Continue PM support for ETSD AI Strategy initiative, AI Portal Project, Courtroom Technology.

- Security & Vulnerability Management

  - Monitor Nessus agent deployment status and coordinate remediation of any remaining gaps.

  - Continue tracking and driving remediation of critical, high, and aging vulnerabilities.

  - Enhance Splunk reporting and validate new asset dashboard data against existing reports.

  - Continue vulnerability trend analysis, POA&M tracking, and documentation development.

  - Support Azure Landing Zone planning and follow-up activities.

- DevSecOps & Automation

  - Evaluate Dockerfile security scanning tools and recommend a standardized enterprise solution.

  - Implement Cosign for container image signing and verification within CI/CD pipelines.

  - Document container security scanning processes and developer implementation guidance.

  - Expand CI/CD deployment capabilities across OpenShift, Azure, and AWS environments.

  - Validate multi-cloud deployment workflows and continue strengthening DevSecOps automation and governance.

- Cloud & Platform Support

  - Continue supporting TSO and COO teams with cloud development, platform administration, and access management activities.

- Courtroom Technology Support

  - Continue FY25 data analysis and preparation of Judiciary-wide reporting deliverables.

  - Support completion of AVoIP courtroom design reviews and comment resolution activities.

  - Continue development of Courtroom Technology SharePoint sites.

  - Provide ongoing research, stakeholder coordination, and technical support for Courtroom Technology initiatives.

  - Continue administration and support of the Judiciary's AVIXA program and related user requests.

### Enterprise Architecture (Support for Call Order 002)

#### Activities planned for the reporting period

- See Call Order 002

#### Activities planned for the following period

- See Call Order 002

### Service Delivery (Support for Call Order 013)

#### Activities planned for the reporting period

- See Call Order 013

#### Activities planned for the following period

- See Call Order 013

## RAE Employee Listing

| Division | RAE Staff | Start Date | TSO LCAT | Supporting Call Order |
| --- | --- | --- | --- | --- |
| Business Ops | Paul Schomburg | 9/15/2024 | Agile Coach/Consultant | CO 16 |
| Business Ops | Parag Matalia | 8/12/2024 | Agile Consultant | CO 16 |
| Business Ops | Ram Dasari | 6/29/2026 | Agile Consultant | CO 16 |
| Business Ops | Jessica Murphy | 9/19/2022 | Admin Support Specialist | CO 16 |
| Business Ops | Andrew Camp | 7/1/2023 | Project Manager | CO 16 |
| Business Ops | Darren Boykin | 7/28/2025 | Information Systems Eng | CO 16 |
| Business Ops | Dora Mensah | 5/12/2025 | Cyber Threat Analyst | CO 16 |
| Business Ops | Benjamin Eseku | 5/19/2025 | Cyber Threat Analyst | CO 16 |
| Business Ops | Pat Shubird | 10/1/2025 | Systems Engineer | CO 16 |
| Business Ops | Prathyusha Gaddam | 10/14/2025 | Information Systems Eng | CO 16 |
| Service Delivery | Joseph Lee | 9/26/2022 | Systems Engineer | CO 16 |
| Service Delivery | Hao Ray Duong | 2/20/2024 | Cloud Architect | CO 16 |
| Business Ops | Pankaj Shishodia | 6/9/2025 | Agile Coach | CO 16 |
| Enterprise Arch | Shamroze Niazi | 9/26/2022 | Enterprise Architect | CO 02 |
| Enterprise Arch | Deloy Johnson | 2/26/2023 | Systems Engineer | CO 02 |
| Service Delivery | Nick Sundar | 12/4/2023 | Enterprise Architect | CO 13 |

## Requested travel during the following reporting period

- N/A

## High Priority Issues

- N/A

## High Priority Risks

- N/A

# Call Order 017 – Enterprise IT Project Management

## Funding Information*

| Funds Obligated | $1,681,420.80 |
| --- | --- |
| Funds Expended to Date | $967,686.39 |
| Funds Remaining | $713,734.41 |
| Estimate at Completion | $1,611,599.59 |
| Over/Under | $69,821.21 |

## Monthly Activity

#### Activities completed for the current reporting period

- Published the June edition of The Agile Pulse Newsletter, continuing regular communications to promote Agile awareness and share practical guidance across the AO.

- Conducted design sessions to define Level 1 of the enterprise Agile training curriculum, establishing the foundation for standardized learning pathways.

- Demonstrated the Learning Hub SharePoint site to the EPMB Branch Chief, highlighting a centralized platform for training materials and resource access.

- Facilitated FY26 Q4 CIO IT Major Project Review presentation training sessions and initiated pre-brief sessions with Program and Project Managers to support review readiness.

- Advanced the ITPM Framework draft for CIO and Chief of Staff review.

- Prepared a draft of the Judiciary Guidelines for Implementing Agile Projects for EPMB Chief review, aligned with the PMBOK v8 framework while maintaining implementation flexibility.

- Developed a draft Project Charter Template and accompanying Instruction Guide to support standardized project initiation practices.

- Continued standardization of EPMB project management templates and tools, reducing duplication, improving consistency, and enhancing the quality of project artifacts.

- Completed FY26 EPMB Q4 planning, including strategic priorities, timeline alignment, resource coordination, and accountability measures.

- Refined the Program and Project Management Community of Practice (CoP) Establishment Outline in preparation for leadership review and approval.

#### Activities planned for the following reporting period

- Continue development and refinement of the enterprise Agile training curriculum and define subsequent training levels and learning pathways.

- Incorporate leadership feedback and advance the Learning Hub SharePoint site toward broader implementation and adoption.

- Complete pre-brief sessions and provide ongoing support for FY26 Q4 CIO IT Major Project Reviews.

- Facilitate review cycles and incorporate stakeholder feedback into the ITPM Framework for finalization.

- Advance the Judiciary Guidelines for Implementing Agile Projects through leadership review and comment resolution.

- Finalize and socialize the Project Charter Template and Instruction Guide for broader EPMB adoption.

- Continue consolidation and standardization of EPMB project management templates, tools, and artifacts.

- Execute the FY26 Q4 work plan and monitor progress against established priorities and milestones.

- Present the Program and Project Management Community of Practice (CoP) outline to EPMB and EPSD leadership and incorporate feedback toward implementation.

- Prepare and publish the July edition of The Agile Pulse Newsletter to maintain stakeholder engagement and Agile awareness.

## Enterprise IT Project Management Employee Listing

| Division | Staff | Start Date | TSO LCAT |
| --- | --- | --- | --- |
| Portfolio Mngt | Taiwo Adenuga | 8/5/2024 | Project Manager |
| Portfolio Mngt | Patti April | 10/28/2024 | Senior Agile Consultant |
| Portfolio Mngt | Bob Carpenter | 3/27/2023 | Agile Coach |
| Portfolio Mngt | Natalee Savage | 7/24/2023 | Agile Coach |
| Portfolio Mngt | Amir Bawani | 1/13/2025 | Agile Coach |
| Portfolio Mngt | Dipika Jain | 11/1/2023 | Agile Coach |
| Portfolio Mngt | Samrah Kashif | 2/17/2026 | Senior Agile Consultant |
| Portfolio Mngt | James Rader | 9/23/2024 | Senior Agile Consultant |

## Requested travel during the following reporting period

- N/A

## High Priority Issues

- N/A

## High Priority Risks

- N/A

# Call Order 018 – Zero Trust Architecture

## Funding Information*

| Funds Obligated | $2,000,000.00 |
| --- | --- |
| Funds Expended to Date | $953,984.81 |
| Funds Remaining | $1,046,015.19 |
| Estimate at Completion | $1,897,591.29 |
| Over/Under | $102,408.71 |

## Monthly Activity

#### Activities completed for the current reporting period

- Completed the structured analysis of interview data for Group 3, expanding As-Is documentation, deepening the Gap Analysis, and refining the list of Zero Trust initiatives for the Application and Workload, Data, and Automation and Orchestration pillars as well as the cross-cutting capabilities for Visibility and Analytics and Automation and Orchestration. The team completed the cost-benefit scoring and prioritization, enabling objective, data-driven recommendations that directly informs the Zero Trust Architecture, Roadmap, and Policy deliverables.

- Continued maturing the Zero Trust Roadmap Document, working closely with government partners to refine structure, visuals, and content for the separate volumes on the initiative details for the Devices and Network pillars and enhancements for the Roadmap main document.  Incorporated feedback received from TSIO members, other SMEs, and the CIOWG.

- Completed the second incremental delivery of the working draft of policies and standards scoped to the Devices and Network pillars. The recommendations align the analysis, its gaps, and initiatives with the required policy or standards needed to support the recommended architecture.  This includes recommendations for Judicial policy, AO manual, standards, and SOPs.

- Expanded the Zero Trust Architecture SharePoint site, strengthening the program’s communications and change-management capability by incrementally adding content. These platforms will improve stakeholder awareness, centralize Zero Trust resources, and increase transparency around program progress and upcoming deliverables.

#### Activities planned for the following reporting period

- Incorporate feedback for the analysis documents, completing the As-Is documentation, the Gap Analysis, and the list of Zero Trust initiatives for the Application and Workload, Data, Visibility and Analytics and Automation and Orchestration pillars. Once the feedback has been incorporated, this completes the work on analysis.

- Deliver the final incremental version of the Zero Trust Roadmap Document, for government review. This final version will include the Roadmap main document, all five CISA ZTMM pillars and the two cross-cutting capabilities for Visibility and Analytics and Automation and Orchestration.

- Deliver the third incremental working draft of policies and standards scoped to the Data and Application and Workload pillars. The recommendations align the analysis, its gaps, and initiatives with the required policy or standards needed to support the recommended architecture.  This includes recommendations for Judicial policy, AO manual, standards, and SOPs.

- Deliver final versions of the RACI, Change Management Plan, and Risk Register for the government review.  The RACI, Change Management Plan, and Risk Register provide the governance backbone that clarifies ownership, drives adoption, and manages risk, directly supporting roadmap execution and ensuring architectural decisions are aligned, actionable, and resilient.

- Continue to expand the Zero Trust Architecture SharePoint site, strengthening the program’s communications and change-management capability by incrementally adding content. These platforms will improve stakeholder awareness, centralize Zero Trust resources, and increase transparency around program progress and upcoming deliverables.

## Enterprise IT Project Management Employee Listing

| Division | Staff | Start Date | TSO LCAT |
| --- | --- | --- | --- |
| Service Delivery | Shawn Faunce | 10/6/2025 | Agile Coach / Consultant |
| Service Delivery | Nat Iyer | 10/14/2025 | Cloud Architect |
| Service Delivery | David Prompovitch | 10/14/2025 | Data Scientist |
| Service Delivery | Mary Raguso | 10/8/2025 | Information Systems Engineer |
| Service Delivery | Megan Giesy | 10/8/2025 | Agile Coach / Consultant |
| Service Delivery | Tapan Rath | 12/29/2025 | Cloud Architect |
| Service Delivery | GyVonda McCain | 2/9/2026 | Systems Integration Engineer |

## Requested travel during the following reporting period

- N/A

## High Priority Issues

- N/A

## High Priority Risks

- N/A

# Contractor GFE Log

| Division | Staff | Barcode | Equipment Type |
| --- | --- | --- | --- |
| Call 002: EA Support |  |  |  |
| Enterprise Arch | Alisa Welch | 7014666 | HP EliteBook |
| Enterprise Arch | Alisa Welch | 7005682 | Docking Station |
| Enterprise Arch | Vidaydhar Tanksale | 4014001 | Dell Latitude 7490 |
| Enterprise Arch | Chris Harkins | 7014315 | HP EliteBook |
| Enterprise Arch | Chris Harkins | 4013022 | MacBook Pro |
| Enterprise Arch | Jason Guglietta | 4016923 | Dell Latitude 7400 |
| Enterprise Arch | Lauryn Holcomb | 7014961 | HP EliteBook |
| Enterprise Arch | Lauryn Holcomb | 7006571 | Docking Station |
| Enterprise Arch | Alec Gura | 7014244 | HP EliteBook |
| Enterprise Arch | Alec Gura | 7006053 | Docking Station |
| Enterprise Arch | Alec Gura | unknown | Mouse, Keyboard |
| Enterprise Arch | Sudeep Telang | 7014386 | HP EliteBook |
| Enterprise Arch | Navin Keswani | 7015184 | HP EliteBook |
| Enterprise Arch | Ranga Lakshminarayanan | 7015474 | HP EliteBook |
| Enterprise Arch | Ramajyothi Indukuri | 7040126 | HP EliteBook |
| Enterprise Arch | Zakariya Saleh | 7040206 | HP EliteBook |
| Enterprise Arch | Yenenesh Shewaneh | 7001927 | HP EliteBook |
| Enterprise Arch | Ceenil Kaur | 7014731 | HP EliteBook |
| Enterprise Arch | Mohammed Khan | 7033645 | HP EliteBook |
| Enterprise Arch | Carl Mosca | 7040339 | HP EliteBook |
| Call 004: MFA Support |  |  |  |
| Enterprise Arch | Sunil Bandapally | 7014300 | HP EliteBook |
| Enterprise Arch | Sunil Bandapally | 700440 | Docking Station |
| Enterprise Arch | Sunil Bandapally | 7004070 | Monitor |
| Enterprise Arch | Sunil Bandapally | 7004082 | Monitor |
| Enterprise Arch | Sangameswar Gupta | 7002171 | HP EliteBook |
| Enterprise Arch | Muhammad Nazir | 4017974 | Dell Latitude 7490 |
| Enterprise Arch | Narayan Verma | 4017395 | Dell Latitude 7480 |
| Enterprise Arch | Karaman Talibov | 7001962 | HP EliteBook |
| Call 013: DevSecOps |  |  |  |
| Service Delivery | Vijay Sivaprakasam | 7015400 | HP EliteBook |
| Service Delivery | Harsh Jain | 7014729 | HP EliteBook |
| Service Delivery | Shailendra Gohil | 7000985 | HP EliteBook |
| Service Delivery | Madhur Gupta | 7014245 | HP EliteBook |
| Service Delivery | Olusola Awoderu | 4012409 | Dell Latitude 7410 |
| Service Delivery | Mohana Molabanti | 7014995 | HP EliteBook 840 |
| Call 015: Innovation & Research |  |  |  |
| Service Delivery | Kenneth Megill | 7014196 | HP EliteBook |
| Service Delivery | Louden Motina | 7001010 | HP EliteBook |
| Service Delivery | Jason de Kock | 7014759 | HP EliteBook |
| Service Delivery | Louie Chen | 7015220 | HP EliteBook |
| Service Delivery | Syed Abbas | 7040110 | HP EliteBook |
| Service Delivery | Dhruvi Rathod | 7015489 | HP EliteBook |
| Call 016: RAE – Business Ops |  |  |  |
| Business Ops | Paul Schomburg | 4017453 | Dell Latitude 7480 |
| Business Ops | Andrew Camp | 7014918 | HP EliteBook 840 |
| Business Ops | Parag Matalia | 7003613 | HP EliteBook |
| Business Ops | Ram Dasari | 7003784 | HP Elitebook |
| Business Ops | Jessica Murphy | 7002351 | HP EliteBook 840 |
| Business Ops | Dora Mensah | 7014185 | HP EliteBook |
| Business Ops | Benjamin Eseku | 7002508 | HP EliteBook |
| Business Ops | Pankaj Shishodia | 7040098 | HP EliteBook |
| Business Ops | Darren Boykin | 7040040 | HP EliteBook |
| Business Ops | Prathyusha Gaddam | 7014391 | HP EliteBook |
| Business Ops | Pat Shubird | 7014631 | HP EliteBook |
| Call 016: RAE Enterprise Architecture |  |  |  |
| Enterprise Arch | Shamroze Niazi | 7014425 | HP EliteBook 840 G10 |
| Enterprise Arch | Shamroze Niazi | 7006312 | Docking Station |
| Enterprise Arch | Shamroze Niazi | 4016225 | MacBook Pro |
| Enterprise Arch | Deloy Johnson | 4018156 | Dell Latitude E7470 |
| Call 016: RAE Service Delivery |  |  |  |
| Service Delivery | Joe Lee | 4014033 | Dell Latitude 7940 |
| Service Delivery | Hao Ray Duong | 7002325 | HP EliteBook 840 |
| Service Delivery | Nick Sundar | 7003586 | HP EliteBook |
| Call 017: Enterprise It Project Management |  |  |  |
| Portfolio Mngt | Taiwo Adenuga | 7003554 | HP EliteBook |
| Portfolio Mngt | Patti April | 7015077 | HP EliteBook |
| Portfolio Mngt | Bob Carpenter | 7003545 | HP VPRO |
| Portfolio Mngt | Natalee Savage | 4017447 | Dell Latitude 7480 |
| Portfolio Mngt | Amir Bawani | 7040159 | HP EliteBook |
| Portfolio Mngt | Dipika Jain | 7015295 | HP EliteBook 840 G10 |
| Portfolio Mngt | Samrah Kashif | 7015105 | HP EliteBook |
| Portfolio Mngt | James Rader | 7003491 | HP EliteBook |
| Call 018: Zero Trust Architecture |  |  |  |
| Service Delivery | Shawn Faunce | 7014336 | HP EliteBook |
| Service Delivery | Megan Giesy | 7040765 | HP EliteBook |
| Service Delivery | Mary Raguso | 7015224 | HP EliteBook |
| Service Delivery | David Prompovitch | 7040450 | HP EliteBook |
| Service Delivery | Nat Iyer | 7014112 | HP EliteBook |
| Service Delivery | Tapan Rath | 7014352 | HP EliteBook |
| Service Delivery | GyVonda McCain | 7014871 | HP EliteBook |
| Laptops Pending Return |  |  |  |
| Service Delivery | Omi Davis | 7014123 | HP EliteBook |

# Billet

| Call 002 (EA) |  |  |  |
| --- | --- | --- | --- |
| Name |  | LCAT |  |
| Alisa Welch |  | Business Analyst - Senior |  |
| Ramajyothi Indukuri |  | Business Analyst - Senior |  |
| Ranga Lakshminarayanan |  | Cloud Architect- CDaaS-PaaS-Cloud Hosting |  |
| Alec Gura |  | Communications Specialist |  |
| Yanenesh Shewaneh |  | Data Architect |  |
| Sudeep Telang |  | Enterprise Architect |  |
| Vidyadhar Tanksale |  | Enterprise Architect |  |
| Carl Mosca |  | System Integration Engineer |  |
| Ceenil Kaur |  | Project Manager |  |
| Christopher Harkins |  | System Integration Engineer |  |
| Jayson Guglietta |  | System Integration Engineer |  |
| Navin Keswani |  | System Integration Engineer |  |
| Zakariya Saleh |  | Systems Architect |  |
| Call 004 (MFA) |  |  |  |
| Name |  | LCAT |  |
| Muhammad Nazir |  | Systems Integration Engineer |  |
| Narayan Verma |  | Systems Integration Engineer |  |
| Sunil Bandapally |  | Systems Integration Engineer |  |
| Lauryn Holcomb |  | Project Manager |  |
| Sangamewar Gupta |  | Systems Integration Engineer |  |
| Karaman Talibov |  | Systems Integration Engineer |  |
| VACANT - Holding |  | Systems Integration Engineer |  |
| Call 013 (DevSecOps) |  |  |  |
| Name |  | LCAT |  |
| Madhur Gupta |  | Business Analyst - Senior |  |
| Vijay Sivaprakasam |  | Systems Integration Engineer |  |
| Harsh Jain |  | Systems Integration Engineer |  |
| Olusola Awoderu |  | Software Engineer |  |
| Shailendra Gohil |  | Systems Integration Engineer |  |
| Mohana Molabanti |  | Software Engineer |  |
| Call 15 (Innovation & Research) |  |  |  |
| Name |  | LCAT |  |
| Louie Chen |  | Artificial Intelligence (AI) Engineer |  |
| VACANT - Holding |  | Artificial Intelligence (AI) Engineer |  |
| VACANT - Holding |  | Software Engineer |  |
| VACANT - but FTE filled by having Syed and Dhruvi FT. |  | Software Developer |  |
| Kenneth Megill |  | Business Analyst - Senior |  |
| Louden Motina |  | Enterprise Architect |  |
| Jason De Kock |  | Systems Integration Engineer |  |
| Syed Abbas |  | Information Assurance Engineer |  |
| Call 16 (RAE) |  |  | Supporting Call Order |
| Name | LCAT |  |  |
| Matalia, Parag | Agile Coach |  | CO 16 |
| Dasari, Ram | Agile Coach |  | CO 16 |
| Schomburg, Paul | Agile Coach |  | CO 16 |
| Murphy, Jessica | Communication Specialist |  | CO 16 |
| Benjamin Eseku | Cyber Threat Analyst |  | CO 16 |
| Mensah, Dora | Cyber Threat Analyst |  | CO 16 |
| Niazi, Shamroze | Enterprise Architect |  | CO 02 |
| Sundar, Nick | Enterprise Architect |  | CO 16 |
| Boykin, Darren | Information Systems Engineer |  | CO 16 |
| Camp, Andrew | Project Manager |  | CO 16 |
| Duong, Ray | Software Engineer |  | CO 16 |
| Johnson, Deloy | Systems Engineer (part time) |  | CO 02 |
| Lee, Joseph | Systems Engineer |  | CO 16 |
| Shishodia, Pankaj | Agile Coach |  | CO 16 |
| Prathyusha Gaddam | Information Systems Engineer |  | CO 16 |
| Shubird, Patrick | Systems Engineer (part time) |  | CO 16 |

| Call 017 (EITPM) |  |
| --- | --- |
| Name | LCAT |
| Adenuga, Taiwo | Project Manager - Mid Level |
| April, Patricia | Agile Coach / Consultant - Senior |
| Carpenter, Robert | Agile Coach |
| Bawani, Amir | Agile Coach |
| Jain, Dipika | Agile Certified Professional |
| Savage, Natalee | Agile Certified Professional |
| Rader, James | Agile Coach / Consultant - Senior |
| Kashif, Samrah | Agile Coach / Consultant - Senior |

| Call 018 (ZTA) |  |
| --- | --- |
| Name | LCAT |
| Shawn Faunce | Agile Coach / Consultant |
| Vacant – Omni Davis | Cloud Architect |
| Nat Iyer | Cloud Architect |
| Tapan Rath | Cloud Architect |
| GyVonda McCain | Systems Integration Engineer |
| David Prompovitch | Data Scientist |
| Mary Raguso | Information Systems Engineer |
| Megan Giesy | Agile Coach / Consultant |

# Resource Movement

| Name | Previous Call Order | New Call Order | LCAT |
| --- | --- | --- | --- |
| n/a |  |  |  |
| New Contractors |  |  |  |
| Name | Start Date | Call Order | LCAT |
| Ram Dasari | 6/29/2026 | CO 16 | Agile Coach |
| Departures |  |  |  |
| Name | Date of Departure | Call Order Departed | LCAT |
| Omni Davis | 5/29/2026 | CO 18 | Cloud Architect |

# Glossary

| Acronym | Definition |
| --- | --- |
| AO | Administrative Office |
| CEA | Chief Executive Architect |
| CI/CD | Continuous Integration / Continuous delivery |
| CIO | Chief Information Officer |
| CIOWG | Court IT Operations Working Group |
| CMM IPT | Case Management Modernization Integrated Project Team |
| CMSO | Case Management Systems Office |
| CSP | Cloud Service Provider |
| CTO | Chief Technology Officer |
| EAMB | Enterprise Architecture Management Board |
| ITSO | IT Security Office |
| JAI | Judiciary Application Inventory |
| JEFS | Judiciary Electronic Filing System |
| MFA | Multi-Factor Authentication |
| PIV-I | Personal Identity Verification Interoperable |
| PMD | Procurement Management Division |
| POC | Proof of Concept |
| SDS | Sealed Document Security |
| SDSO | Systems Development and Support Office |
| SOW | Statement of Work |
| TRM | Technical Reference Model |
| VPN | Virtual Private Network |
| WHfB | Windows Hello for Business |